## BurnDownTable
|  |  |  | STORY POINTS |  | 1 = | 10 hour |  | 130 in total |  |  | 1300 hours in total |  |  | BOTH RELEASES
|  | Backlog | Days | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
|  | In Progress | Actual Burndown | 100 | 97 | 94 | 91 | 89 | 86 | 83 | 80 | 75 | 70 | 66 | 64 | 61 | 58 | 55 | 52 | 49 | 45 | 42 | 39 | 35 | 34 | 32 | 30 | 30 | 28 | 25 | 21 | 19 | 17 | 16 | 14 | 12 | 11 | 9 | 7 | 5 | 3 | 3 | 1 | 0
|  | Done | Ideal Burndown | 100 | 97.5 | 95 | 92.5 | 90 | 87.5 | 85 | 82.5 | 80 | 77.5 | 75 | 72.5 | 70 | 67.5 | 65 | 62.5 | 60 | 57.5 | 55 | 52.5 | 50 | 47.5 | 45 | 42.5 | 40 | 37.5 | 35 | 32.5 | 30 | 27.5 | 25 | 22.5 | 20 | 17.5 | 15 | 12.5 | 10 | 7.5 | 5 | 2.5 | 0
|  | Feature | Estimated Hours & Points | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39 | Day 40
Sprint1 | Release 1 | Registration | 80 / 8 | Complete | Day 1: 1; Day 2: 1; Day 3: 1; Day 4: 2; Day 5: 2; Day 6: 1 | 8
|  | Welcome page setup and implementation | 90 / 9 | Complete | Day 7: 2; Day 8: 1; Day 9: 2; Day 10: 1; Day 11: 1; Day 12: 1; Day 14: 1 | 9
|  | Unique user Requirements | 90 / 9 | Complete | Day 5: 1; Day 6: 1; Day 7: 1; Day 9: 1; Day 10: 2; Day 13: 1; Day 14: 1 | 8
|  | City Information | 70 / 7 | Complete | Day 15: 1; Day 16: 1; Day 17: 1; Day 18: 2; Day 19: 2; Day 20: 1 | 8
Sprint2 |  | Admin Account | 40 / 4 | Complete | [40 empty] | 2 | bar: Day 16 to Day 17
Sprint1 |  | Account Type Requirements | 20 / 2 | Complete | [40 empty] | 2 | bar: Day 12 to Day 13
Sprint2 |  | Personalised User Interface | 40 / 4 | Complete | [40 empty] | 4 | bar: Day 11; Day 14; Day 16; Day 20
|  | Administrator creation of admin accounts | 20 / 2 | Complete | [40 empty] | 2 | bar: Day 3; Day 12
|  | View information from different user types | 40 / 4 | Complete | [40 empty] | 1 | bar: Day 1
Sprint1 |  | Database Information | 20 / 2 | Complete | Day 1: 1; Day 15: 1; Day 17: 2; Day 18: 1 | 5
|  | Website Aesthetics | 40 / 4 | Complete | [40 empty] | 3 | bar: Day 8; Day 13; Day 15
Sprint2 |  | Other City Information | 40 / 4 | Complete | Day 19: 1; Day 20: 2 | 3
Sprint1 |  | Additional cities | 40 / 4 | Complete | Day 2: 2; Day 9: 1; Day 10: 1 | 4
|  | Database Scalability | 30 / 3 | Complete | [40 empty] | 3 | bar: Day 3; Day 6; Day 9
Sprint2 |  | Map Readability | 40 / 4 | Complete | [40 empty] | 3 | bar: Day 22 to Day 23; Day 37
|  | Web Links to services | 20 / 2 | Complete | [40 empty] | 1 | bar: Day 21
|  | Database Security | 20 / 2 | Complete | [40 empty] | 3 | bar: Day 22 to Day 23; Day 37
|  | Search Field | 20 / 2 | Complete | [40 empty] | 2 | bar: Day 34 to Day 35
|  | Remember Username | 20 / 2 | Complete | Day 8: 3; Day 24: 2; Day 25: 1 | 6
|  | Additional Account Information | 20 / 2 | Complete | [40 empty] | 2 | bar: Day 25; Day 39
|  | Admin Map Access | 20 / 2 | Complete | [40 empty] | 2 | bar: Day 25; Day 40
|  | Generation of location pages | 80 / 8 | Complete | Day 26: 2; Day 27: 1; Day 28: 1; Day 29: 1; Day 32: 1; Day 33: 1; Day 36: 1 | 8
|  | Location Search | 20 / 2 | Complete | [40 empty] | 3 | bar: Day 28; Day 30; Day 39
|  | Search Results | 20 / 2 | Complete | Day 31: 2 | 2
|  | Interactive Mapping System | 60 / 6 | Complete | [40 empty] | 6 | bar: Day 27; Day 29; Day 32; Day 34 to Day 36
Release 2 |  | Live System Information | 80 / 8 | In Progress | [40 empty] | 0
|  | Calendar integration | 40 / 4 | In Progress | [40 empty] | 0
|  | Gps Integration | 40 / 4 | In Progress | [40 empty] | 0
|  | Social Media Integration | 40 / 4 | In Progress | [40 empty] | 0
|  | Recommendations | 40 / 4 | In Progress | [40 empty] | 0
|  | Incentives | 40 / 4 | In Progress | [40 empty] | 0
|  | Mobile Devices | 20 / 2 | In Progress | [40 empty] | 0
1300